## Sheet1
item | Test plan Name | Required Document | SZ VAL Owner | Test location | Test Plan | 文档名称 | 用例数 | 5G | 测试总结 | 测试报告 | owner（第一轮学习） | Deadline | Status | Reviewed Status
1 | Android Platform Test Plan | TECC&DRR | zitao.chen@tcl.com | RD/US | Y | REQ: Reqs-Android.docx Test Plan: Android Platform Test Plan.docx Test Report: U50 Plus_Android Platform Testplan_TECC&DRR_Test Report_Modify By CD.xlsx | 75 | 0 | CD-Create | SZ-update | Luo Yang | 2019-12-04 | Done | OK
2 | unified settings |  | zitao.chen@tcl.com | RD | N | REQ: Reqs-Android.docx (Page: 137_1.2.60.2.1.1) Test Plan: N/A Test Report: U50 Plus_Unified Setting Test Report_Commercialization TECC_Test Report_Modify By CD.xlsx | 88 | 0 | CD-Create | SZ-update | Luo Yang | 2019-12-04 | Done | OK
3 | LTE_PowerOnActivation_TestPlan(POA) | TECC | shaofang.wang@tcl.com | US | Y | REQ: 1. Reqs-Activation-UserInterface 2. Reqs-LTE-PCO 3. Reqs-LTE-Power On Activation Ergo: 1. Postpaid Ergo 2. Prepaid Ergo 3. UICC card message Test Plan: LTE-PowerOnActivation_Test Plan Test Report:Test report_POA_U50A PLUS VZW | 25 | 0 | CD-Create | SZ | Li Xiaofeng | 2019-11-29 | Done | OK
4 | MMS VZW test plan | TECC | lei.deng@tcl.com | US | Y | Test Plan: MMS_TestPlan.docx REQ: Reqs-VZW-MultiMediaSpecifications (2).docx Test Report: U50 Plus_MMS TestPlan_TECC_20190218 | 42 | 0 | No need | SZ | Wang Yunqing | 2019-11-29 | Done | OK
5 | DoU | Commercialization TECC | hehua.ding@tcl.com | 国内-Tool | TBD | [5 empty] | Tool-Yue Chengkun | 2019-12-06 | N/A
6 | Idle Data Usage Test Plan | DRR&Commercialization TECC | lei.xie@tcl.com | US | Y | Test Plan: Idle Data Usage Test Plan.docx No REQ document Test Report: U50 Plus_Idle Data Usage Test Plan_DRR&Commercialization TECC_20190218 | 1 | 0 | CD-Create | SZ | Wang Yunqing | 2019-11-29 | Done | OK
7 | Hidden menu | DRR | zitao.chen@tcl.com | RD | N | test report: U50APLUSVZW_hidden_code_v0.6 - VZW | N/A | 0 | No need | SZ | Li Sha | 2019-11-29 | Done | OK
8 | VoLTE Inter Client Test Plan |  | yuanpeng.hu@tcl.com | US | Y | REQ: N/A Test Plan: VoLTE Inter Client Test Plan.docx Test Report: VoLTE Inter Client Test Report_Modify By CD.xlsx | 21 | 0 | CD-Create | SZ-update | Luo Yang | 2019-12-09 | Done | OK
9 | PlatformSecurity Test Plan | Commercialization TECC | wzhou2@tcl.com | RD | Y | Test plan: PlatformSecurity Test Plan.docx REQ: Reqs-PlatformSecurity.docx test report:Project name_PlatformSecurity Test Plan_Commercialization TECC_Date | 23 | 0 | CD-Create | SZ-update | Li Sha | 2019-11-29 | Done | OK
10 | OBDM Tool Test Plan | Commercialization TECC | menglu.chen@tcl.com | RD | Y | REQ: N/A Test plan: 1. OBDM Tool Test Plan.docx 2. OBDM Tool Auto Test Test report:1. OBDM Tool Test Report 2. OBDM Tool Auto Test report | 14 | 0 | CD-Create | SZ | Wu Di | 2019-12-03 | Done | OK
11 | VZW Cloud Test Plan | Commercialization TECC | baiyong.chen@tcl.com | US | Y | REQ: 1. Reqs-VZWCloudApplication 2. Setup Wizard Cloud Screens.pdf Test plan: VZW Cloud Test Plan.docx Test report: VZW Cloud Test Report | 86 |  | SZ-update | SZ | Wu Di | 2019-12-18 | Done | OK
12 | Software Upgrade Assistant Test Plan | Commercialization TECC | peigui.qin@tcl.com | RD | Y | REQ: (无正式需求文档)1. SUA-UI.zip 2. SUA&SURA User Guide test plan: Software Upgrade Assistant Test Plan.docx test report:Software Upgrade Assistant Test Plan | 12 | 0 | CD-Create | SZ | Wu Di | 2019-12-04 | Done | OK
13 | VICE_Field_Test_V0 4 |  | hangtian.liang@tcl.com | US | Y | REQ: N/A Test Plan: VICE_Field_Test_V0 4.docx Test Report: VICE File Test Report_Create By CD.xlsx | 6 | 0 | CD-Create | CD-Create | Luo Yang | 2019-12-09 | Done | OK
14 | Reverse Logistics Test Plan | Commercialization TECC | lei.deng@tcl.com | RD | Y | REQ: N/A test plan: 1. Reverse Logistics Test Plan.docx 2. SUGAR售后工具操作指引 test report: Reverse Logistics Testing Test Plan.xlsx | 10 | 0 | CD-Create | SZ | Wu Di | 2019-12-04 | Done | OK
15 | LABLIVEVOWIFI | TECC | wen.xia@tcl.com | US | Y | No REQ document Test Plan: End To End Voice Over Wi-Fi.docx Test Report: U50 Plus_LABLIVEVOWIFI Test Plan_TECC_20190214.xlsx | 5 | 0 | No need | SZ | Wang Yunqing | 2019-12-06 | Done | OK
16 | LTE E911 E2E | TECC | qifeng.zhao@tcl.com | US (Lab） | Y | REQ: N/A Test Plan: 1. LTE-E911_LTEOnlyOrLTEMulti-Mode Devices Test Plan.docx 2. Test Plan_E911_LTE Only or LTE Multi-ModeDevice_FieldTest.docx 3. Test Plan_E911_LTE Only or LTE Multi-ModeDevice_E2E.docx Test Report: E911E2E Test Report_Create By CD.xlsx | 155 | 0 | CD-Create | CD-Create | Luo Yang | 2019-12-13 | Done | OK
17 | Three OTA sample report for RA at Phase 1 | DRR | ying.duan@tcl.com | US | N | REQ: Test Plan: Test Report: U50 Plus_Three OTA sample report for RA_DRR_20190531.xlsx | 3 | 0 | No need | SZ | Li Xiaofeng | 2019-12-06 | Done | OK
18 | Confirmation of OTA SU software download Results | Commercialization TECC | ying.duan@tcl.com | RD | N | Test Report: U50 Plus_OTA SU software download Results_Commercialization TECC_2019021….xlsx | 0 | 0 | No need | SZ | Li Xiaofeng | 2019-12-18 | Ongoing | NOK:需要写测试总结：需要确认清楚，报告中的用例来源；
19 | Daylight Savings Time (DST) | Commercialization TECC | zitao.chen@tcl.com | RD | N | REQ: N/A Test Plan: N/A Test Report: U50 Plus_Daylight Saving Time(DST) Test Report_Commercialization TECC_20190219.xlsx | 9 | 0 | CD-Create | SZ | Luo Yang | 2019-12-10 | Done | OK
20 | OTA Software update, EUT, SUA/SRA | Commercialization TECC | peigui.qin@tcl.com | RD | N | Test Report: U50 Plus_Software Upgrade Assistant Test Plan_Commercialization TECC_201....xlsx | 0 | 0 | No need | SZ | Li Xiaofeng | 2019-12-06 | Done | OK

## Sheet2
1 | 2 | 3 | 4 | 5
二
三
ass